## Sheet1
Date | Bug | Description(summary) | Notes | Type | Fixed? | Fixed by whom | Verified by whom
2018-06-19 | Medusa will fly. | Medusa will float in place if terrain beneath her is deleted. | Only happens if you try to load a level without a text file of the level | Gameplay | Medusa as a moveable character has been removed from the game
2018-06-19 | Medusa won't reset. | Medusa will not reset her position between levels. | Only happens if you try to load a level without a text file of the level | Gameplay | Medusa as a moveable character has been removed from the game
2018-06-19 | Can't see anything. | Lighting makes it extremely difficult to see traps and objects on path. | Lighting is temporary. Blake will fix 6th milestone. | Aesthetic | Lava has been removed from the game
2018-06-19 | Medusa doesn't turn properly. | Medusa turns to face enemies very sporadically and also rotates along Z axis when she shouldn't. |  | Gameplay | Medusa as a moveable character has been removed from the game
2018-06-19 | Rebuilding a level won't build properly. | Tiles are being built, but aren't being rotated properly. I think grid also won't update properly as well. |  | Gameplay | Yes | Andy | Travis
2018-06-19 | Menu button on level select map is broken. | When you click on menu button on the level select map, it closes the whole level select map while on the menu. |  |  | Menu button has been removed
2018-06-20 | Medusa won't die | Currently she has no hp value. This is a gameplay bug more in that it has not been implemented yet. |  | Gameplay | Medusa as a moveable character has been removed from the game
2018-06-20 | Some traps missing textures | Some traps we have implemented are textureless. | Will be replaced with correctly texture models at the beginning of milestone 6 | Texture/Material | Yes. The spike trap was the culprit and had its texture adjusted | Lee | Travis
2018-06-20 | Monster Models Missing | the prefabs for the monsters are missing when they spawn in | when we add the new monster models, this should hopefully fix this problem | Gameplay | Unable to replicate
2018-06-20 | Enemy pathing problem | Enemies hug tight corners as they walk causing them to miss traps placed on corners | Add more padding to navmesh | Gameplay | Yes. Changed their angular speed from 180 to 60 and this seems to be a good speed. | Lee | Travis
2018-06-20 | Level Select Stars | Each set of stars needs to be wired to reflect the achieved score for each level |  | Gameplay | Done. Replaying a previous level wont update stars yet. | Lee | k-dawg
2018-06-20 | Tutorial name issue | The tutorial still refers to the game as Record Wreckers |  | Text Problem | Tutorial has been removed from the game
2018-06-20 | Load Time Issues | After clicking play on the tittle screen, there is a noticeable load time | We need to implement some kind of load screen | Gameplay | Yes. Loadscreen rewired | Lee | Travis
2018-06-26 | Mines Double-Attack | Enemies can be hit twice by the same mine. | Second hit seems to happen just before the mine vanishes. Seems to be triggering a second time if enemies are on top of it just before it disappears. | Gameplay | Yes, shortened amount of time between trap triggering and the same trap disappearing. | Travis | Travis
2018-06-26 | Upgrade/Sell Stays | Upgrade/Sell menu does not deactivate upon victory or loss. |  | UI | Yes | Lee | Travis
2018-06-26 | Level does not reset | Going between levels can cause the UI to not activate, and traps and other aspects will not be reset. |  | Gameplay/UI | Yes | Andy | Travis
2018-07-05 | Load screen still not working | Recurring bug |  | Gameplay
2018-07-05